PROPOSAL / 2026 Project Proposal A clear plan for the work, the people and the outcome.

PREPARED WITH PLOT DOCS   •   EDIT EVERY SECTION   •   SAVE AS DOCX OR PDF

# At a glance

| CLIENT | PROJECT LEAD | TIMELINE | BUDGET |
| --- | --- | --- | --- |
| Northstar Labs | Avery Chen | 8 weeks · Jan–Mar | $48,000 |
| Sponsor: Jordan Lee | Design: Priya Shah | Kickoff: 12 Jan | Payment: milestone |

## Executive summary

Northstar Labs is launching a customer education hub to shorten onboarding and make product expertise available on demand. This proposal covers a focused eight-week engagement: discovery, content architecture, a production-ready site and a measurement plan.

OUTCOME WE ARE BUYING A launch-ready learning hub that takes a new customer from sign-up to first value in under 15 minutes, with a clear baseline for measuring adoption.

## Objectives

Reduce time-to-first-value for new accounts by at least 30%.

Publish 12 core learning paths with consistent structure and search.

Instrument every path so the team can see completion and drop-off.

Leave the team with an editorial system they can run without us.

## Scope

| IN SCOPE | OUT OF SCOPE |
| --- | --- |
| Discovery interviews and content audit | Paid media and campaign production |
| Information architecture and templates | Translations beyond English |
| 12 learning paths, 40–60 articles | Ongoing community management |
| Analytics events and handover workshop | Custom LMS procurement |

## Timeline

| WEEK | WORKSTREAM | MILESTONE |
| --- | --- | --- |
| 1 | Discovery | Interview notes and content inventory |
| 2–3 | Architecture | Approved sitemap and page templates |
| 4–6 | Production | First six paths in review |
| 7 | Measurement | Events live in staging |
| 8 | Launch | Handover, QA and go-live |

## Budget

| WORKSTREAM | DAYS | INVESTMENT |
| --- | --- | --- |
| Discovery and strategy | 6 | $7,200 |
| Content architecture | 5 | $6,000 |
| Content production | 18 | $21,600 |
| Design and build | 9 | $10,800 |
| Measurement and handover | 2 | $2,400 |
| Total | 40 | $48,000 |

## Next steps

Confirm the sponsor and subject-matter experts for discovery.

Approve the timeline and milestone payment schedule.

Book the kickoff workshop and share existing content.