## Tracker
Project Tracker
One view of what is moving, what is blocked and who owns the next step.
Task | Owner | Status | Priority | Start | Due | % done | Days left | Notes
Finalise launch brief | Avery | Done | High | 2026-10-01 | 2026-10-06 | 100% |  | Approved by sponsor
Homepage copy | Priya | In progress | High | 2026-10-05 | 2026-10-18 | 70% |  | Awaiting legal review
Pricing page build | Sam | In progress | Medium | 2026-10-08 | 2026-10-22 | 45% |  | Desktop done
Customer quotes | Mei | Blocked | Medium | 2026-10-09 | 2026-10-20 | 20% |  | Waiting on approvals
Press kit | Jordan | Not started | Low | 2026-10-15 | 2026-10-27 | 0% |  | Assets ready
Analytics QA | Avery | In progress | High | 2026-10-12 | 2026-10-24 | 60% |  | Events in staging
Launch rehearsal | Team | Not started | High | 2026-10-26 | 2026-10-29 | 0% |  | Book the room
OPEN TASKS |  |  | BLOCKED |  |  | AVG. COMPLETE
Formulas:
Days left = IF([Due]="","",[Due]-TODAY())